## User_Stories
	Iteration 1	Iteration 2	Iteration 3	Iteration 4	Iteration 5

ID	Story Title	Points	As a/an	I want	So that		Notes
			Sales rep
S1	Upload Picture	3	Sales rep	to take a picture of a side of the house	I can start to edit the windows on that side
S2	Select Window	5	Sales rep / Installation Crew	select a specific window on the picture	I can customize the window
S3	Customize Window	8	Sales rep	Customize the window	I can preview finished product on the house
S4	Edit Border	2	Sales rep	To edit the border of a window (trace)	I can make the border the proper size
S5	Manual Add	5	Sales rep	To manually add a new window	I can select and preview changes to this window
S6	Remove Window	2	Sales rep	To remove a window	The window's border is no longer on the preview
S7	Save Window	2	Sales rep	To save an *individual window	The window details are saved for later
S8	Save Project	2	Sales rep	To save the *entire set of windows	The entire set of windows are saved
S9	CRUD Client	8	Sales rep / Admin	all CRUD functionality for client information	I have CRUD functionality for client information
S10	CRUD Project	8	Sales rep / Admin	all CRUD functionality for projects	I have CRUD functionality for projects
S11	CRUD Project Detail	8	Sales rep / Admin	all CRUD functionality for project details	I have all CRUD functionality for project details

			Admin (Office Manager)
S12	CRUD Account	8	Admin	all CRUD functionality for employee accounts	I have all CRUD functionality for accounts
S13	Search Projects	2	Admin	To search for a specific project	I can see information related to that project
S14	Compact View	3	Admin	A compact view of some of the project's details	I can get a succinct view of the project's details
S15	Detailed View	3	Admin	A detailed view of some of the project's details	I can see all information related to this project
S16	Assign Project	3	Admin	To assign a project to an installation crew (member)	The project has a crew assigned to it for completion

			Installation Crew
S17	View Assigned Projects	2	Installation Crew	To view all projects assigned to me / my crew	I can see which projects are assigned to me / my crew
S18	Select Project	2	Installation Crew	To select a project that has been assigned to me / my crew	I can select which project me / my team is going to work on
S19	Input Final Window Measurements	3	Installation Crew	Input the final measurements for specific windows in the project	The project has accurate measurements

			Customer
S20	View Project Status	3	Customer	to view my project's status bar given the link (email / text message)	I can be kept up to date with my project's progression

		82

NFRS	THE	SHALL HAVE	WITH THIS FEATURE	OR THIS CONSTRAINT

NFR1	UI	Colors	that match the company's colors (white & blue)
NFR2	Window Designer	Automated pricing	that will generate a rough estimate of how much that window will cost
NFR3	Window Designer	Automated measuring	that will generate a rough estimate of the dimensions of the window
NFR4	System	A database	that uses PostgreSQL
NFR5	CRM	Push notifications	that tell the customer when their project's status has updated
NFR6	System	Front end logic	Written in HTML, JavaScript, CSS, React
NFR7	System	Back end logic	Written in Python

## Tasks
ID	Task Title	Task Description	Story ID

## Epics
ID	Epic Title	Description